## Slide 1: MIS321
Agile Grooming and Planning

## Slide 2: Learning Objectives
Understand the elements of a product backlog and what traits lead to the strongest deliverables
Dive into prioritization and learn different methods for understanding what is the most important feature or item to work on
Explore estimation and the different practices and measures that are used today
Understand story points and planning poker as ways to discern the level of effort and complexity
Learn the other inputs that affect the planning process
Evaluate Sprint planning and XP planning game to learn how commitments are made and work is planned
See how maintenance work can be incorporated into Agile teams
Review the triple constraints model and how it is handled within the Agile framework

## Slide 3: Grooming the Backlog
D.E.E.P.
  Detailed - The highest priority stories have sufficient detail for the development team to deliver them. OK for lower priority items to be at “epic” level.
  Estimated – The team understands the stories and believes there is adequate information to estimate the level of effort
  Emergent – Backlog is constantly evolving
  Prioritized – Backlog always sits in priority order

## Slide 4: Prioritization
Value Based
  Increased revenue, decreased cost, improved customer service, etc.
  What happens if we don’t take action? Market place perception, regulatory issues, etc.
Value Steam Mapping
  Taken from Lean manufacturing
  Map process from customers perspective looking at where the experience is less than optimal

## Slide 5: Prioritization
MoSCoW
  Must Have
  Should Have
  Could Have
  Want to have
Kano Model
  Basic Needs
  Performance Needs
  Delights
  Over time features move from one category to another

## Slide 6: Estimating
Level of Effort (LOE)
  Quick and easy
  Not very useful in more detailed planning
  Often used as a “first pass estimation”
Ideal Time (Days / Hours / Work Sessions)
  Time needed given no interruptions
  Conversion factor of 2:1 is common

## Slide 7: Estimating
Hours
  Advantage is it’s the most detailed and accurate
  Disadvantage is it’s the most detailed and accurate
Story Points
  Good understanding of size without binding expectations of hours
  Fibonacci Sequence: 1, 2, 3, 5, 8, 13, 21
  Story points don’t translate well from one team to the next
  Accurate once velocity is established.
  Using a know effort to establish relative values.
  Estimate includes design, dev and test (definition of done)

## Slide 8: Team Participation in Estimating and Planning
Planning Poker
  www.planningpoker.com
  Chance to continue the conversation
Wide-Band Delphi
  More accurate
  More time consuming

## Slide 9: Prepping for Sprint Planning
Backlog Grooming
  Well written stories
  Understood
  Estimated (definition of done)
  Prioritized
Determining Velocity
Technical Debt
Undocumented Features (aka bugs)

## Slide 10: Sprint Planning
Use this session to make sure everyone has a complete understanding of the user stories.
Decide which stories will be included in the sprint.
Break the stories into individual tasks.
Assign the tasks to individual team members.
Estimate, in hours, how long each task will take.

## Slide 11: Questions?