## Slide 1: MIS321
Methodologies

## Slide 2: Agenda
Methodology
  What and Why
  Categories
    Plan Driven
    Agile
    When to use each
  History of Agile

## Slide 3: What is a Methodology
A body of practices, procedures, and rules used by those who work in a discipline
  Process
  Artifacts
  Terms
  What else?
Notes: What – problem that we’re trying to solving
Why – value that we’re adding
Who – Members of the team/client/etc.
How – Methodology

## Slide 4: Why Is It Important
Guide Post
  Provide structure in a chaotic world
Ability to Scale
Reuse
More Predictable Results
Reduce Costs / Risks
31% of all projects are cancelled before completion
88% of projects run over schedule, over budget or both
52% of projects will cost 189% of their original estimates
Average time overrun is 222% of original estimates

## Slide 5: Model of Group Development
Created by Bruce Tuckman

## Slide 6: Plan Driven Methodologies
Formalized process with well defined stages
Plan, analyze (requirements), design, develop, test, implement, support
Document THEN Implement
Examples include Waterfall, ADM, SDLC, etc.
Follows the cadence of deployments

## Slide 7: Plan Driven Methodologies
Notes: If you’ve ever tried walking with your eyes closed or if you’re walking and distracted looking at your phone, it’s easy to veer off course OR to have the course change
Walking example:
I need to walk from here to that point on the wall.
I will spend a while to measure the distance, measure my stride, estimate how long it will take me
Then, I will create my plan. I need to take 9 steps to get from here to there, and it will take me 30 seconds
I close my eyes and start to walk.

## Slide 8: Agile Methodologies
Structured but informal process
Process repeated frequently
Generate stories, code, test, repeat
Implement THEN Document
Examples include Scrum, XP, Crystal, FDD
Notes: Agile is the response to that
Same problem to solve: From here to the wall
But much smaller chunks / fewer steps – repeated more frequently

## Slide 9: Agile Methodologies
Notes: Take three steps; measure distance, measure stride, estimate length of time to get there – just 10 seconds
Take the three steps, then look up: how did the actuals compare to the estimates? Am I still on track? Verify with stakeholders: are we still aiming for the same place?

## Slide 10: Plan Driven Vs Agile
 | Plan-Driven | Agile
Development Model | Formal, traditional 6-7 stage life cycle | Based on a repeated series of short iterations
Early Project Risk | All project uncertainty can be managed before design & development begins. | All project uncertainty cannot be managed upfront. Only the uncertainty in the first iteration is managed.
Late Project Risk | Not expected. If scope changes happen, the new uncertainty is managed in its entirety all at once. | Expected. Uncertainty is managed as it arises.
Formal Coordination Mechanisms |  | 
Planning | All planning can be complete at once during the early stages of the project. If scope changes arise, a new complete set of plans is developed. | Because systems emerge, planning can only take place via short-term iterations.
Project Team Structure | Mechanistic (formal and unchanging). Divisional (each team member performs separate and independent roles). | Organic (flexible and cooperative). Cross-functional (team members belong to functional groups as well with occasional switching between groups)
Project Team Roles | Formal and unchanging. | Informal. Roles will often change as the requirements change.
Informal Coordination Mechanisms |  | 
Project Team Advice Network | Advice-sharing relationships develop vertically (between supervisors and supervisees). There is no need to seek advice horizontally. | Advice-sharing relationships develop both vertically and horizontally.
Use of Knowledge | Codified and explicit. It’s discovered via training, manuals, and expert systems. | Tacit. Relies on having knowledge experts who are willing and able to share their knowledge

## Slide 11: Which Should I Use
Consideration | Plan Driven | Agile
Well defined requirements | X | 
Unlimited customer access |  | X
High project team turnover | X | 
High potential for scope creep / evolving requirements |  | X
Many experts |  | X
Large team | X | 
High project complexity | X | X
Culture of empowerment |  | X
Virtual teams | X | X

## Slide 12: History of Waterfall Methodologies
Emerged in the 50’s
Advocates sequential phases of development
First and most popular model
  Fits with organizational hierarchy
  Taken from other fields (construction, manufacturing)
  Fits well with outsourcing model

## Slide 13: Waterfall Criticisms
Process heavy
Unresponsive to change
Little room for user feedback
Long development cycles

## Slide 14: History of Agile Development
Agile is an overarching term that includes iterative approaches to software development that embrace the values of the Manifesto for Agile Software Development.
Not new
  IBM was using iterative approaches as early as 1957
  Today includes methodologies such as XP, Scrum and Kanban

## Slide 15: Comparing Agile Methodologies
Agile Methodology | Emphasis | Founder(s)
Extreme Programming | Efficiency, customer focus and feedback, and quality | Kent Beck
Scrum | Teaming, organizing work | Jeff Suthewwrland and Ken Schwaber
Feature-Driven Development | Interactive development of user-focused features | Jeff DeLuca
Dynamic Systems Development Method | Structured approach to rapid development, collection of best practices | DSDM Consortium
Lean Software Development | Eliminate work that does not create customer value | Mary and Tom Poppendieck
Kanban Method | Visualize and manage workflow, just-in-time development | David Anderson
Cyrstal Family | People, communication, process rigor maps to product and organization dynamics | Listair CockburnAi

## Slide 16: Extreme Programming (XP)
First used at Chrysler in 1996
Developed in an attempt to release quality code faster and more efficiently
Introduction of Test Driven Development (TDD)

## Slide 17: Extreme Programming (XP)
Key themes include:
  Frequent releases
  Pair programming
  Regular builds
  Quality
  Simplicity of code
  Rapid and regular feedback

## Slide 18: Scrum
Originally developed in 1993.
Tends to focus primarily on the “teaming” or project management aspects of Agile.
Focuses on time boxing work to create a sense of urgency.
Each time box is referred to as a “sprint”. Shippable code is produced at the end of each sprint.

## Slide 19: Scrum
Product Owners maintain a prioritized list of requirements in a product backlog.
Requirements take the form of user stories.
Daily stand-ups or “scrums” are held to track progress.
The Scrum Master helps remove outside distractions and ensures daily scrums stay on point.

## Slide 20: Scrum
Daily scrums take the form of:
  What have I done since yesterday
  What am I doing today
  What roadblocks do I foresee
Team updates tasks daily to generate burn down charts

## Slide 21: Feature Driven Development
Originally developed in 1997 by Jeff De Luca
Planning and development focus on the specific features that address customer requirements.
Unlike other Agile methods, the development plan is based on ordering features and assigning them to classes.

## Slide 22: Dynamic Systems Development Method
Originally developed in 1994 to add structure to RAD.
RAD focuses on creating prototypes as efficiently as possible.
DSDM focuses on the project management aspects of Agile
Requirements are deemed as “must, should, could and won’t haves”

## Slide 23: Lean Software Development
First book on the topic appeared in 2003
Stems from Lean manufacturing which is built on the idea that all process and resources must directly contribute to creating something of value to the customer
Seven key principles are: Eliminate waste, Amplify learning, Decide as late as possible, Deliver as fast as possible, Empower the team, Build integrity in, See the whole

## Slide 24: Kanban
Developed by David Anderson in an attempt to build a “just in time” software delivery system
Kanban translates to “signboard” in Japanese.
Six core principles:
  Visualize workflow
  Limit work in progress
  Manage the flow through the system
  Provide explicit policies
  Improve collaboratively
  Ensure feedback

## Slide 25: Crystal Family
Advocates that when a team is using an iterative process, the amount of structure should be tailored to the dynamics of the team.
“No two crystals are the same”

## Slide 26: Questions?